## Slide 1: Chapter 22 – Project Management

## Slide 2: Software project management
Concerned with activities involved in ensuring that software is delivered on time and on schedule and in accordance with the requirements of the organisations developing and procuring the software.
Project management is needed because software development is always subject to budget and schedule constraints that are set by the organisation developing the software.

## Slide 3: Success criteria
Deliver the software to the customer at the agreed time.
Keep overall costs within budget.
Deliver software that meets the customer’s expectations.
Maintain a coherent and well-functioning development team.

## Slide 4: Factors influencing project management
Company size
Software customers
Software size
Software type
Organizational culture
Software development processes
These factors mean that project managers in different organizations may work in quite different ways.

## Slide 5: WBS - Definition
A deliverable oriented grouping of project elements which organizes and defines the total scope of the project. Each descending level represents an increasingly detailed definition of a project component.

## Slide 7: Why is it needed?

## Slide 8: Agenda Work Breakdown Structure
Work Breakdown Structure—What is it?
Defining Activities (Summary Tasks)
Defining Tasks
More Examples

## Slide 9: Work Breakdown Structure
It is a hierarchical description of the work that must be done to complete the project
It defines all of the activities that must be carried out in order for you to complete the project
Each activity has a number of tasks needed to be done in order to complete it

## Slide 10: Work Breakdown Structure
Activity: an item of work needed to meet the requestor’s requirements
Task: a smaller item of work

## Slide 11: Work Breakdown Structure
The tasks that you define in your Work Breakdown Structure are what you will put into MSProject
For each task, you will assign resources, an estimate of how long that task will take, and the dependencies (i.e. is a task dependent on another one to finish before it can start?)

## Slide 12: Work Breakdown Structure
Resource
Task
Activity
Milestone
Duration

## Slide 13: Work Breakdown Structure
There are (at least) 4 uses for the WBS:
  Thought Process Tool
  Architectural Design Tool
  Planning Tool
  Project Tracking and Reporting Tool

## Slide 14: Work Breakdown Structure
Thought Process Tool
  A design and planning tool
  Project Manager and team can visualize exactly how the work of the project is defined and managed effectively

## Slide 15: Work Breakdown Structure
Architectural Design Tool
  A picture of the work of the project and how the tasks relate to one another.

## Slide 16: Work Breakdown Structure
Planning Tool
  Take the tasks that need to be done to develop the project and estimate effort, elapsed time and resources
  Build a schedule of when the work will be done – will show project completion

## Slide 17: Work Breakdown Structure
Project Tracking and Reporting Tool
  Shows visually what is happening and when – it is used for reporting status
  Shows how much of a specific task is completed

## Slide 18: WBS Extract

## Slide 19: Agenda
Work Breakdown Structure—What is it?
Defining Activities (Summary Tasks)
Defining Tasks
More Examples

## Slide 20: Defining Activities
How to define Activities (Summary Tasks):
  There are various methods used:
    Top Down
    Team
    Bottom Up

## Slide 21: Defining Activities
Top Down
  Start at a goal (activity) level and break down the work to lower levels (tasks). An activity may involve many steps (tasks) and many people (resources) being assigned to that one activity. It is important to break down to the lowest level task so that only one resource is assigned to that task.

## Slide 22: Defining Activities
Top Down
  Once you are down to the lowest level task you can sequence the tasks so that some can be done in parallel. This will allow you to save time on the overall project.

## Slide 23: Defining Activities
Team
  Assign team members various part of the overall project to determine the work breakdown structure for that section of the project. It may involve using the top-down approach at this point in time to build the detailed schedule.

## Slide 24: Defining Activities
Bottom Up
  More like a brain-storming session. Not very organized.
  Start with the goal and as a large group identify the tasks needed to be completed.
  Tasks are written down. When no more task suggestions are made then the group tries to organize the tasks into like groupings.
  Very inefficient.

## Slide 25: Defining Activities
We will use: Top Down
  We will start with activities or summary tasks such as use cases, database creation, and so on, and break these into tasks

## Slide 26: Defining Activities
Different approaches to defining activities:
  Noun approach
    e.g. functional decomposition (activities around building each use case or database creation)
  Verb approach
    e.g. common activities, from a project methodology e.g. design, build, test, document

## Slide 27: Defining Activities
We will define activities that will identify a significant deliverable
    Use case
    Database
    Documentation
    System testing
    Acceptance testing

## Slide 28: Agenda
Where are we?
Work Breakdown Structure—What is it?
Defining Activities (Summary Tasks)
Defining Tasks
More Examples

## Slide 29: Defining Tasks
Once you have decided on your activities (summary tasks), you need to define the sub tasks needed for each activity.

## Slide 30: Defining Tasks
Each task in your WBS must meet the following six criteria:
1. Status/Completion is measurable
  For your plan, make tasks small enough so you can use a binary measure: done or not done
2. Start/End clearly defined
  Just give MSProject the duration; it will compute the start and end dates. We will provide MSProject with a project start date only.

## Slide 31: Defining Tasks
Task criteria continued:
3. Task has a deliverable
  Makes it easier to track; gives it validity
4. Time/Cost easily estimated
  Smaller tasks are easier to estimate

## Slide 32: Defining Tasks
Task Criteria Continued
5. Duration is within acceptable limits
  Shorter tasks are easier to manage (problems become apparent very quickly)
  Tasks must be less than 10 hours
6. Tasks are independent
  One person per task (except for meetings)

## Slide 33: Defining Tasks
Keep refining your task hierarchies until you are satisfied that you have covered al of the work that needs to be done in order to get your project completed

## Slide 34: Agenda
Where are we?
Work Breakdown Structure—What is it?
Defining Summary Tasks
Defining Tasks
More Examples

## Slide 35: Build Dog House

## Slide 36: Build Dog House

## Slide 37: Paint Room

## Slide 38: Paint Room

## Slide 39: A Small System

## Slide 40: A Small System

## Slide 41: A Small System

## Slide 42: Example
You have decided to relocate to a new apartment on November1st. Identify the activities and tasks that are necessary to complete this move.
  Identify activities (summary tasks)
  Identify tasks within activities

## Slide 43: Example
Identify the tasks that need to be done to do requirements gathering. Do not consider doing Business Use Case Diagrams or Business Use Case Descriptions.